## Sheet1
PID Drive - Osamah & Minh | PID Rotaton - Robel & Vivek | Game Plan - Mathieu
Goals
Reliably move forward/backward a set number of tiles | Reliably turn cw/ccw a given angle in degrees | Figure out a step by step game plan (including parameter values i.e. tiles & degree values) that incorporates the two functions being built.
Figure out the value of the ticksPerTile constant - Mathieu | Figure out the value of the ticksPerDegree constant - Either Vivek/Robel | Focus on the scoring of mobile goals, find the most efficient path.
Parameters
int numberOfTiles | int degrees (-360 to 360) cw and ccw respectively | Approx. time to completion
int speed (between 0 - 127) |  | # of points achieved
Important Dates
2018-01-22 | Verbal update over Slack/Upload progress code on GitHub | Verbal update over Slack - Show written work & any calculations you used to determine values.
2018-01-25 | Show progress to me at the shop | In person update, same as above
2018-02-01 | COMPLETED code shown to me at the shop | Completed and ready to test